## Sheet1
| Madlena | Mladen | Toma | Ivaylo
What we did well
| Ivaylo planned good the work that needs to be done | Using and understanding of the basic framework from class | Good communication | Good understanding and overcoming difficulties
| Good communication | Work with GitHub improved | Good cooperation in the team | Team spirit is high
|  | Reusing components created by other team mates | Working with GitHub
managed to comply with deadline
What can be improved
| Tool for team member's tasks and their details | Better task distribution and organization |  | Tools not aligned
|  | Improve communication even more |  | Too much new things and lack of experience
Action items
<Mladen> Update README.md with project conventions and tools
<Toma> Create Google doc/excel with project tasks assignment and details
Slack, Microsoft teams - better tools for communication and collaboration